## Cover
Arogya Diagnostics — User Stories
Module-wise backlog of user stories derived from the live codebase (React + Express + Postgres monorepo). Generated 2026-05-14.
How to use
• Each module has its own sheet. The 'All stories' sheet is a single-table view across modules. • Story columns: ID, Role, User story (As a … I want … so that …), Acceptance criteria, Priority (MoSCoW), Status. • Status reflects what is observable in the code as of generation date — Implemented / Stub / TODO etc. • Priority follows MoSCoW: Must, Should, Could.
Module index
1. Public Marketing Site | 10 stories
2. Authentication & Identity | 10 stories
3. Patient Dashboard | 8 stories
4. Doctor Appointment Booking | 5 stories
5. Test / Package Booking | 7 stories
6. Payments (Manual UPI) | 9 stories
7. Reports / Lab Results | 6 stories
8. Invoices | 5 stories
9. Admin Dashboard & Analytics | 6 stories
10. Admin Bookings | 4 stories
11. Walk-in Bills | 4 stories
12. Catalog: Categories | 1 stories
12. Catalog: Services | 2 stories
12. Catalog: Departments | 1 stories
12. Catalog: Pincodes | 2 stories
13. Doctor Management | 5 stories
14. Slot Generation | 4 stories
15. Home Collection | 5 stories
16. Notifications | 6 stories
17. Audit Log | 3 stories
18. Patients Records | 4 stories
19. Settings | 2 stories
20. Cart | 3 stories
21. Cross-cutting / NFR | 8 stories

## 1. Public Marketing Site
ID | Role | User story | Acceptance criteria | Priority | Status
PUB-01 | Visitor | As a visitor, I want a homepage with hero, services snapshot, doctors snapshot, testimonials, and contact CTA so I can quickly understand what the clinic offers. | Hero with clinic name + tagline; sections for services, doctors, departments, reviews; bilingual EN/BN service names; CTA buttons for Book / Call / WhatsApp. | Must | Implemented
PUB-02 | Visitor | As a visitor, I want to browse all diagnostic services and health packages filtered by category and free-text search so I can find what I need. | GET /services?category_slug=&q= returns active services only; ILIKE on name; ordered by display_order; max 200 results. | Must | Implemented
PUB-03 | Visitor | As a visitor, I want a service detail page with description, prep instructions, sample type, turnaround time and price so I can decide before booking. | GET /services/:slug; renders full_details, prep_instructions, sample_type, report_turnaround_hours, price; Book Test CTA adds to cart. | Must | Implemented
PUB-04 | Visitor | As a visitor, I want to browse all verified doctors filtered by department and search so I can pick the right specialist. | GET /doctors?department_id=&q= filters role=doctor + is_verified + is_active; ordered by rating_avg desc; LIMIT 100. | Must | Implemented
PUB-05 | Visitor | As a visitor, I want a doctor profile page with photo, qualifications, departments, consulting centers, schedule preview and reviews so I can choose confidently. | GET /doctors/:id + GET /reviews?doctor_id=; photo via public /doctors/:id/photo blob; reviews limited to status=approved. | Must | Implemented
PUB-06 | Visitor | As a visitor, I want to browse clinical departments and their associated doctors so I can navigate by speciality. | GET /departments + GET /departments/:slug; active departments only; ordered by display_order. | Should | Implemented
PUB-07 | Visitor | As a visitor, I want a contact form to send the clinic an enquiry without signing up so I can ask questions easily. | POST /enquiries with name/email/phone/subject/message; rate-limited 5/min/IP; inserts row with status=new. | Must | Implemented
PUB-08 | Visitor | As a visitor, I want to leave feedback / a review for the clinic or a doctor so future patients can read it. | POST /reviews with star rating + text; status=pending (admin moderation); rate-limited 5/min/IP. | Should | Implemented
PUB-09 | Visitor | As a visitor, I want privacy and terms pages so I can understand how my data is used. | Static pages at /privacy and /terms accessible without login. | Should | Implemented
PUB-10 | Visitor | As a visitor, I want a Book Home Visit CTA in the header so I can start a home-collection booking immediately. | Header button sets cartStore.preferredVisitType='home_visit' and navigates to /services?mode=home_visit; Services page shows banner with reset option. | Should | Implemented

## 2. Authentication & Identity
ID | Role | User story | Acceptance criteria | Priority | Status
AUTH-01 | Patient | As a new patient, I want to sign up with first/last name, mobile, optional email and password so I can manage my bookings. | POST /auth/signup; mobile regex ^[6-9]\d{9}$; password ≥6; rejects duplicate mobile/email; returns JWT + user. | Must | Implemented
AUTH-02 | Patient | As an existing patient, I want to log in with email and password so I can access my dashboard. | POST /auth/login; bcrypt verify; checks is_active && is_login_enabled; updates last_login_at; returns JWT + user. | Must | Implemented
AUTH-03 | Patient | As a patient without a password, I want to log in with mobile + OTP so I don't need to remember credentials. | POST /auth/otp/send returns 6-digit code (debug_code in non-prod); POST /auth/otp/verify accepts code + optional names; auto-creates patient row if mobile is new. | Must | Implemented (OTP via SMS provider TODO)
AUTH-04 | Patient | As a logged-in patient, I want to view my profile (name, mobile, email, DOB, gender, default address) so I can keep it current. | GET /auth/me returns full user row; rendered on /dashboard/profile. | Must | Implemented
AUTH-05 | Patient | As a logged-in patient, I want to update my profile fields including default address JSON so future bookings prefill correctly. | PATCH /me with profileUpdateSchema; dynamic SET builder; default_address stored as JSONB. | Must | Implemented
AUTH-06 | Patient | As a logged-in patient, I want to change my password so I can rotate credentials. | POST /auth/change-password; current_password verified if existing hash; new_password hashed via bcrypt. | Should | Implemented
AUTH-07 | Patient | As a logged-in patient, I want to log out from the header dropdown so my JWT is cleared from the device. | Best-effort POST /auth/logout + clears arogya-jwt localStorage + zustand state. | Must | Implemented
AUTH-08 | Admin | As an admin/super_admin, I want a separate /admin/login route so my login experience is distinct from the patient flow. | AdminLoginPage; same POST /auth/login; on success redirects to /admin and RequireAuth checks role admin¦super_admin. | Must | Implemented
AUTH-09 | Any role | As any logged-in user, I want my JWT to be re-validated on every request so revoking an account takes effect immediately. | requireAuth middleware re-reads users row by sub claim; sets req.user; rejects with 403 ACCOUNT_DISABLED when is_active=false. | Must | Implemented
AUTH-10 | Patient | As a patient who got auto-logged out (401), I want my JWT cleared automatically so /auth/me doesn't loop. | Axios response interceptor clears token on 401 then propagates the error. | Should | Implemented

## 3. Patient Dashboard
ID | Role | User story | Acceptance criteria | Priority | Status
PD-01 | Patient | As a patient, I want a dashboard overview showing upcoming bookings, pending payments and recent reports so I get a one-glance status. | DashboardOverviewPage uses useMyBookings()/useMyReports() to render KPI cards + next-appointment + recent-reports. | Must | Implemented
PD-02 | Patient | As a patient, I want a dedicated Appointments page listing my doctor bookings so I can track them. | GET /bookings filtered by booking_type=doctor_appointment; each row shows doctor_name, speciality, center, status badge. | Must | Implemented
PD-03 | Patient | As a patient, I want a dedicated Tests page listing my test/package bookings so I can track sample collection and results. | GET /bookings filtered to test_booking; row shows items_summary, collection_status, reports_count. | Must | Implemented
PD-04 | Patient | As a patient, I want a combined My Bookings page if I prefer one stream view. | MyBookingsPage at /dashboard/bookings unifies both booking types ordered by scheduled_date desc. | Should | Implemented
PD-05 | Patient | As a patient, I want to open a booking detail page from any list to see items, payment status, address, advance/balance and reports. | GET /bookings/:id; ownership-checked; renders items, payments, active reports with download links. | Must | Implemented
PD-06 | Patient | As a patient, I want to cancel an upcoming booking from its detail page if my plans change. | POST /bookings/:id/cancel sets booking_status=cancelled and records cancelled_at + optional reason. | Must | Implemented
PD-07 | Patient | As a patient, I want a Reports page that lists all my lab results across bookings so I can find them in one place. | GET /reports patient-scoped; ReportsPage thumbnails + download via signed URL. | Must | Implemented
PD-08 | Patient | As a patient, I want a clear status sub-line like 'Advance ₹100 paid · Balance ₹100 due at visit' instead of generic status text. | BookingStatusBadge takes paymentStatus + totalAmount + advanceAmount and renders contextual sub-line; threaded through all dashboard pages. | Should | Implemented

## 4. Doctor Appointment Booking
ID | Role | User story | Acceptance criteria | Priority | Status
DA-01 | Patient | As a patient, I want to pick a doctor's available date and time slot from a live calendar so I don't book a conflicting slot. | GET /doctors/:id/slots?date=&center_id=&visit_type=; live generator reads doctor_centers.schedule, subtracts existing bookings + doctor_unavailability; returns {time, available, reason}. | Must | Implemented
DA-02 | Patient | As a patient, I want to enter or confirm my contact details and address for the appointment. | Step 2 of BookDoctorPage uses patientInfoSchema; prefills from useAuthStore user when present. | Must | Implemented
DA-03 | Patient | As a patient, I want a clear breakdown of consultation fee, advance (50%) and balance so I know what I'm paying. | subtotal = doctor.consultation_fee; advance = round(total/2); balance = total - advance; rendered in checkout summary. | Must | Implemented
DA-04 | Patient | As a patient, I want to submit the booking with a UPI payment proof image/PDF so my slot is locked immediately. | POST /bookings/doctor-appointment (multipart) inserts bookings + booking_items(doctor_consultation) + invoices (trigger numbers it) + payments(upi_manual, captured, verified_at=NULL) in one transaction. | Must | Implemented
DA-05 | Patient | As a patient, I want a no-consulting-center guard so I'm not allowed to book a doctor whose schedule isn't set up yet. | BookDoctorPage shows friendly message when doctor.centers[] is empty. | Should | Implemented

## 5. Test - Package Booking
ID | Role | User story | Acceptance criteria | Priority | Status
TB-01 | Patient | As a patient, I want to add multiple tests/packages to a cart with quantities so I can check out in one go. | useCartStore items[] persists to localStorage 'arogya-cart'; supports addItem, removeItem, updateQuantity, subtotal, count. | Must | Implemented
TB-02 | Patient | As a patient, I want to pick in-clinic vs home collection per booking so I can choose how the sample is taken. | Step 2 of BookTestPage switches visit_type; home_visit branch reveals address + pincode check + slot picker. | Must | Implemented
TB-03 | Patient | As a patient, I want to enter my pincode and instantly see if home collection is serviceable + the home-visit charge. | GET /serviceable-pincodes/check?pincode= validates regex; returns {serviceable, city, home_visit_charge, collection_lead_time_hours}. | Must | Implemented
TB-04 | Patient | As a patient, I want to pick a home collection time slot if my pincode is serviceable. | GET /home-collection/slots?date=&pincode= currently returns hardcoded 8-slot grid (STUB); hook is enabled only when pincode confirmed. | Must | Stub (hardcoded slots)
TB-05 | Patient | As a patient, I want a clear breakdown showing items × qty, subtotal, home-visit charge, total, advance and balance. | Step 3 renders summary; advance = round((subtotal + home_visit_charge)/2). | Must | Implemented
TB-06 | Patient | As a patient, I want to submit my test booking with a UPI payment proof so my slot is reserved immediately and the invoice is auto-generated. | POST /bookings/test (multipart) inserts bookings + N booking_items + invoices + payments(upi_manual) atomically; redirects to /payment/callback. | Must | Implemented
TB-07 | Patient | As a patient, I want my home-visit preference to survive navigation from Services → Cart → Booking. | cartStore.preferredVisitType persists; BookTestPage reads it for initial visit-type state. | Should | Implemented

## 6. Payments (Manual UPI)
ID | Role | User story | Acceptance criteria | Priority | Status
PAY-01 | Patient | As a patient at checkout, I want to see the clinic's UPI VPA + QR code so I can pay from any UPI app. | GET /clinic/upi returns {upi_id, upi_display_name} from clinic_settings; UpiPaymentModal renders QR via react-qr-code and copy-VPA button. | Must | Implemented
PAY-02 | Patient | As a patient, I want to attach a screenshot or PDF of the UPI confirmation (with optional UTR) so my booking is captured. | FormData: payment_proof (≤5 MB, jpeg/png/webp/pdf) + data (JSON booking payload) + optional upi_reference; backend validates via validateProofFile(). | Must | Implemented
PAY-03 | Patient | As a patient, I want to view the proof I uploaded inside my booking detail page so I can confirm what I sent. | GET /payments/:id/proof streams BYTEA (own-only); ProofPreview renders image or PDF embed. | Should | Implemented
PAY-04 | Admin | As an admin, I want a Payment Re-Verify queue listing all upi_manual payments with verified_at IS NULL so I can clear them at sample-collection / clinic-visit. | GET /admin/payments/pending-re-verify; partial index payments_pending_reverify_idx; AdminLayout bell badge shows count. | Must | Implemented
PAY-05 | Admin | As an admin, I want to view the uploaded proof in a large modal alongside booking metadata + optional notes textarea before approving. | ReVerifyPaymentModal with proof full-bleed + booking sidebar + notes; calls GET /admin/payments/:id/proof. | Must | Implemented
PAY-06 | Admin | As an admin, I want re-verify to be idempotent so double-clicking doesn't break anything. | POST /admin/payments/:paymentId/re-verify uses CTE WHERE verified_at IS NULL; second call returns already-verified row. | Must | Implemented
PAY-07 | Patient | As a patient, I want my booking status to read 'In progress' until admin re-verifies, then automatically update to 'Confirmed'. | Booking status transitions in_progress → confirmed; verified_at populated; cache invalidation propagates to patient hooks. | Must | Implemented
PAY-08 | Admin | As an admin, I want to record an offline payment (cash, UPI QR offline, card swipe, cheque) against an existing booking so partial payments can be added later. | POST /admin/bookings/:id/payments uses FOR UPDATE lock; recomputes paid/balance/payment_status from SUM(amount-refunded_amount). | Must | Implemented
PAY-09 | System | As the system, I want to keep Razorpay stubs for later reintroduction so we can switch back without rewriting. | POST /bookings/:id/confirm-payment-stub + POST /payments/create-order + POST /webhooks/razorpay (no signature verify yet) all preserved. | Should | Preserved as stub

## 7. Reports - Lab Results
ID | Role | User story | Acceptance criteria | Priority | Status
RPT-01 | Admin | As an admin, I want to look up a booking by its human-readable booking_code (AROGYA-TEST-YYYYMM-NNNNNN) so I can upload reports without typing numeric IDs. | GET /admin/booking-lookup?code=; returns id + patient_snapshot + items_summary + doctor_name. | Must | Implemented
RPT-02 | Admin | As an admin, I want to upload multiple report files (PDF/image/DICOM/Word/ZIP - any format) for a booking with a chosen report_type. | POST /admin/bookings/:bookingId/reports (multer 25 MB cap, no MIME whitelist); version = MAX+1 per booking; no soft-disable of prior versions. | Must | Implemented
RPT-03 | Admin | As an admin, I want a standalone /admin/reports page that lists recent reports across bookings with thumbnails + preview + delete actions. | GET /admin/reports?q=&limit= joins reports + bookings; AdminReportsPage shows 48×48 thumbnail or file icon, action buttons. | Should | Implemented
RPT-04 | Admin | As an admin, I want to soft-delete a report so it disappears from the patient's view but stays for audit. | DELETE /admin/reports/:reportId sets is_active=FALSE; cache invalidation hits admin list + patient myReports + booking detail. | Must | Implemented
RPT-05 | Patient | As a patient, I want to download my report via a short-lived signed URL so the file is protected. | GET /reports/:id/download (uploads route) returns {url, expires_in:900} via storage.getSignedUrl; downloadReport() opens new tab. | Must | Implemented
RPT-06 | System | As the system, I want reports for walk-in bookings to be allowed even when no patient user exists. | Migration 0023: reports.patient_user_id is NULLABLE; ownership is via booking_id; upload handler still populates when booking has a user. | Must | Implemented

## 8. Invoices
ID | Role | User story | Acceptance criteria | Priority | Status
INV-01 | System | As the system, I want every booking (online doctor / online test / walk-in) to auto-create exactly one invoice with a generated number on INSERT. | INSERT invoices(invoice_number='') inside the same booking transaction; generate_invoice_number trigger fills INV-YYYYMM-NNNNNN (Asia/Kolkata). | Must | Implemented
INV-02 | Patient | As a patient, I want to download my own invoice as a PDF from my booking detail page. | GET /bookings/:id/invoice.pdf (own-only); shared streamInvoicePdf() helper; A4 PDF via pdfkit. | Must | Implemented
INV-03 | Admin | As an admin, I want to list all invoices with filters (type/origin/from/to/free-text) so I can find them quickly. | GET /admin/invoices?type=&origin=&from=&to=&q= joins invoices + bookings; max 500 rows; ILIKE on invoice_number, booking_code, patient_snapshot JSON keys. | Must | Implemented
INV-04 | Admin | As an admin, I want per-row download of the invoice PDF from the invoices list. | GET /admin/bookings/:id/invoice.pdf delegates to streamInvoicePdf(); same PDF as patient download. | Must | Implemented
INV-05 | System | As the system, I want the invoice header/footer to reflect current clinic settings (name, address, phone, email, GSTIN). | PDF reads clinic_settings; clinic_address JSON flattened to 'line1, line2, city, state, pincode'. | Should | Implemented

## 9. Admin Dashboard & Analytics
ID | Role | User story | Acceptance criteria | Priority | Status
DSH-01 | Admin | As an admin, I want a dashboard with today's bookings, today's revenue, pending reports, new patients this week and yesterday comparison. | GET /admin/dashboard returns kpis + schedule; computes today/yesterday boundaries in Asia/Kolkata; revenue from payments (captured-refunded). | Must | Implemented
DSH-02 | Admin | As an admin, I want the dashboard to auto-refresh so I can keep it open as a live operations screen. | useAdminDashboard refetchInterval: 60_000 ms. | Should | Implemented
DSH-03 | Admin | As an admin, I want today's schedule of the next 10 bookings with doctor + items summary on the dashboard. | schedule[] subquery returns 10 rows with inline doctor_name and items_summary via string_agg. | Must | Implemented
DSH-04 | Admin | As an admin, I want an Analytics page showing daily revenue + booking trend, top services, type/origin/status/payment-method distributions over the last N days. | GET /admin/analytics?days=N (1-365); Promise.all-fans-out 7 queries; generate_series ensures empty days are charted. | Should | Implemented
DSH-05 | Admin | As an admin, I want to export analytics to CSV so I can share with stakeholders. | Multi-section CSV built client-side via Blob URL (KPIs + daily trend + top services + status + payment methods). | Should | Implemented
DSH-06 | Admin | As an admin, I want the heavy analytics charts lazy-loaded so the rest of the app stays light. | AnalyticsPage uses React.lazy in App.tsx; chunk is ~119 kB gzipped. | Could | Implemented

## 10. Admin Bookings
ID | Role | User story | Acceptance criteria | Priority | Status
AB-01 | Admin | As an admin, I want a filterable bookings list (by type, origin, status, free-text) so I can find rows fast. | GET /admin/bookings?type=&origin=&status=&q=&visit_type=; subqueries inline doctor_name + items_summary; LIMIT 200 ORDER BY created_at desc. | Must | Implemented
AB-02 | Admin | As an admin, I want to open a booking detail page showing items, payments, active reports, advance/balance and the patient snapshot. | GET /admin/bookings/:id; full booking + items + payments + active reports. | Must | Implemented
AB-03 | Admin | As an admin, I want to change a booking's status (pending_payment / confirmed / in_progress / completed / cancelled / no_show) from a color-coded dropdown both in the list and the detail sidebar. | PATCH /admin/bookings/:id/status; BookingStatusSelect compact + default variants; invalidates admin + patient caches. | Must | Implemented
AB-04 | Admin | As an admin, I want to filter by visit_type (in_clinic vs home_visit) so I can split the worklist. | visit_type filter on /admin/bookings and /admin/invoices; SELECT also returns b.visit_type for origin pill. | Should | Implemented

## 11. Walk-in Bills
ID | Role | User story | Acceptance criteria | Priority | Status
WB-01 | Admin | As a receptionist, I want a Create Walk-in Bill page where I can capture patient (snapshot or existing user), N line items (catalog or custom), and optional payment in one form. | POST /admin/walk-in-bills with discriminated-union walkInItemSchema; single transaction creates booking + items + optional payment + invoice. | Must | Implemented
WB-02 | Admin | As a receptionist, I want walk-in bookings to use today's date/time and skip slot generation so I can bill quickly. | INSERT bookings with booking_origin='walk_in', visit_type='in_clinic', scheduled_date=today, scheduled_start_time=now, collection_status='not_required'. | Must | Implemented
WB-03 | Admin | As a receptionist, I want the bill to automatically compute subtotal, total, paid, balance, payment_status and booking_status so I don't make arithmetic mistakes. | Backend computes payment_status (pending¦partial¦paid) and booking_status (completed if paid in full else in_progress). | Must | Implemented
WB-04 | Admin | As a receptionist, I want offline payment captured atomically with the booking so the invoice numbers correctly. | INSERT payments(payment_source='offline', payment_status='captured', collected_by_user_id=req.user.id) when payment.amount > 0; invoice trigger fires. | Must | Implemented

## 12. Catalog- Categories
ID | Role | User story | Acceptance criteria | Priority | Status
CAT-01 | Admin | As an admin, I want full CRUD over service categories with auto-slug, duplicate detection, soft delete, and a doctors/services count badge. | GET/POST/PATCH/DELETE /admin/service-categories[/:id]; FK on services.category_id is ON DELETE RESTRICT so deletes are soft (is_active=FALSE). | Must | Implemented

## 12. Catalog- Services
ID | Role | User story | Acceptance criteria | Priority | Status
CAT-02 | Admin | As an admin, I want full CRUD over services + health packages with category dropdown, auto-slug, package toggle (package_service_ids + discount %), and soft delete. | GET/POST/PATCH/DELETE /admin/services[/:id]; services_package_consistency_chk enforced by always sending [] for package_service_ids on package rows. | Must | Implemented
CAT-03 | Admin | As an admin, I want unique slug + test_key conflicts surfaced as friendly 409 messages so I know which field collides. | Pre-checks both UNIQUE constraints and returns 409 DUPLICATE with the offending column. | Should | Implemented

## 12. Catalog- Departments
ID | Role | User story | Acceptance criteria | Priority | Status
CAT-04 | Admin | As an admin, I want CRUD over departments with auto-slug, doctor count, and soft delete. | GET/POST/PATCH/DELETE /admin/departments[/:id]; FK users.department_id ON DELETE SET NULL but soft-delete pattern used. | Must | Implemented

## 12. Catalog- Pincodes
ID | Role | User story | Acceptance criteria | Priority | Status
CAT-05 | Admin | As an admin, I want CRUD over serviceable pincodes (with city/state/zone/home_visit_charge/lead_time) so home collection is correctly scoped. | GET/POST/PATCH/DELETE /admin/serviceable-pincodes[/:id]; pincode field disabled in edit (natural key); soft delete. | Must | Implemented
CAT-06 | System | As the system, I want a deactivated pincode to immediately stop being bookable for home collection. | Public /serviceable-pincodes/check filters WHERE is_active=TRUE; no extra work needed. | Must | Implemented

## 13. Doctor Management
ID | Role | User story | Acceptance criteria | Priority | Status
DR-01 | Admin | As an admin, I want to list all doctors (including inactive) with department filter, search, photo avatar, and centers count. | GET /admin/doctors?q=&department_id=&is_active=; centers_count subquery; DoctorAvatar per row. | Must | Implemented
DR-02 | Admin | As an admin, I want to add a doctor with profile (name, speciality, qualifications, consultation fee, about, department) and one or more consulting centers in a single submit. | POST /admin/doctors with nested centers[]; transaction inserts users(role=doctor,is_login_enabled=FALSE) + N doctor_centers. | Must | Implemented
DR-03 | Admin | As an admin, I want to upload a doctor's profile photo and have it served back at a public URL for marketing pages. | POST /admin/doctors/:id/photo (5 MB, JPG/PNG/WEBP); writes BYTEA + MIME; GET /doctors/:id/photo public stream with Cache-Control max-age=300. | Must | Implemented
DR-04 | Admin | As an admin, I want to add/edit/soft-delete a doctor's consulting centers including a visual Weekly Schedule editor with slot duration, buffer, lunch. | POST /admin/doctors/:id/centers, PATCH/DELETE /admin/centers/:centerId; WeeklyScheduleEditor emits WeeklySchedule JSON matching doctor_centers.schedule shape. | Must | Implemented
DR-05 | Admin | As an admin, I want a separate home-visit schedule per center so a doctor can do clinic visits on some days and home visits on others. | doctor_centers.home_visit_schedule JSONB; reads in slot generator when visit_type=home_visit. | Should | Implemented

## 14. Slot Generation
ID | Role | User story | Acceptance criteria | Priority | Status
SLOT-01 | System | As the system, I want to generate slots live from the doctor's schedule, subtracting existing bookings and unavailability blocks, so admins manage availability through the schedule editor. | Slot generator reads schedule/home_visit_schedule for weekday, generates from {start,end,slot_minutes,buffer_minutes,lunch_start,lunch_end}, subtracts active bookings + doctor_unavailability. | Must | Implemented
SLOT-02 | Admin | As an admin, I want to block whole days or specific slots for a doctor via doctor_unavailability so vacations and emergencies are respected. | doctor_unavailability rows: NULL slot_start_time = whole day; NULL doctor_center_id = all centers. | Should | DB ready, no admin UI yet
SLOT-03 | System | As the system, I want to prevent double-booking via a partial unique index on (doctor_user_id, doctor_center_id, scheduled_date, scheduled_start_time). | uq_active_slot partial unique index covers booking_status IN (draft, pending_payment, confirmed, in_progress). | Must | Implemented
SLOT-04 | System | As the system, I want a cron to expire stale drafts so slot locks are released. | Flag stale draft bookings whose slot_locked_until has passed to cancelled. | Should | TODO (noted in migration)

## 15. Home Collection
ID | Role | User story | Acceptance criteria | Priority | Status
HC-01 | Admin | As an admin, I want CRUD over home collector accounts (phlebotomists) including name, mobile, DOB (for age), gender, photo, active toggle. | GET/POST/PATCH/DELETE /admin/collectors; users row with role='patient'+admin_role='collector' or similar; photo uploaded as BYTEA via /admin/collectors/:id/photo. | Must | Implemented
HC-02 | Admin | As an admin, I want a Home Collection Board (Kanban) showing each home-visit booking by collection_status so I can dispatch fast. | HomeCollectionBoardPage groups bookings by collection_status: not_assigned → assigned → en_route → collected → received_at_lab. | Must | Implemented
HC-03 | Admin | As an admin, I want to assign a collector to a not_assigned booking via a dropdown directly on the board. | useUpdateCollection mutation sets collection_status='assigned' + assigned_staff_user_id; useCollectionStaff() feeds dropdown. | Must | Implemented
HC-04 | Admin | As an admin, I want to progress a collection through stages so the patient and lab are kept in sync. | PATCH /admin/home-collections/:id transitions collection_status through assigned → en_route → collected → received_at_lab. | Must | Implemented
HC-05 | Patient | As a patient, I want to see the assigned collector's name, age, phone and photo on my booking page so I know who is coming. | Booking detail surfaces assigned_staff metadata (full name, age computed from DOB, mobile, photo URL). | Should | Implemented

## 16. Notifications
ID | Role | User story | Acceptance criteria | Priority | Status
NOTIF-01 | System | As the system, I want a notifications table that supports both per-user and admin-broadcast rows so the bell can show targeted + clinic-wide events. | Migration 0026: notifications + notification_reads; audience IN (admin, patient, collector); partial indexes for hot paths (unread + admin broadcasts). | Must | Implemented
NOTIF-02 | Admin / Patient | As an admin or patient, I want a bell icon in my header with an unread badge so I can see new events at a glance. | NotificationBell variants light (patient header) / dark (admin layout); badge shows count capped at 9+. | Must | Implemented
NOTIF-03 | Admin / Patient | As an admin or patient, I want the bell to poll the server every 30s and refetch on tab focus + on open so I see fresh events. | useMyNotifications polls; dropdown open also invalidates ['notifications','mine']. | Should | Implemented
NOTIF-04 | Admin / Patient | As an admin or patient, I want to click a notification to mark it read and deep-link to the related entity. | useMarkNotificationRead; broadcasts use notification_reads table; non-broadcast use read_at column; click triggers Link to n.link. | Must | Implemented
NOTIF-05 | Admin / Patient | As an admin or patient, I want a Mark All Read button to bulk-clear my unread count. | useMarkAllNotificationsRead. | Should | Implemented
NOTIF-06 | System | As the system, I want notifications fired for proof_submitted, reverified, collector_assigned, collection_status_changed so users are informed of state changes. | Backend domain events INSERT notifications with appropriate event + link + audience. | Must | Implemented

## 17. Audit Log
ID | Role | User story | Acceptance criteria | Priority | Status
AUDIT-01 | System | As the system, I want every successful authenticated mutating request (POST/PATCH/PUT/DELETE 2xx) automatically logged with actor, action, entity, IP and user-agent. | auditLogMiddleware hooks res.on('finish'); classify() derives action from URL (e.g. services.create, payments.re-verify); SKIP_PATTERNS exclude auth/me/health/webhooks. | Must | Implemented
AUDIT-02 | Super Admin | As a super_admin, I want an admin audit-log page to review who did what when. | AdminAuditLogPage uses GET /admin/audit-log; filters by actor, action, entity, date range. | Should | Implemented
AUDIT-03 | System | As the system, I want audit failures to never break the real action. | INSERT is fire-and-forget after res.finish; errors are logged via pino, not propagated. | Must | Implemented

## 18. Patients Records
ID | Role | User story | Acceptance criteria | Priority | Status
REC-01 | Admin | As an admin, I want a Patients page listing all patient users with mobile, last login, booking count so I can support them. | AdminPatientsPage queries /admin/patients (assumed). | Should | Implemented
REC-02 | Admin | As an admin, I want to moderate reviews (pending → approved/rejected/hidden) with optional rejection_reason and clinic_reply. | AdminFeedbackPage reads pending reviews; reviews table tracks status, clinic_reply, replied_at, replied_by. | Should | Implemented
REC-03 | Admin | As an admin, I want to triage enquiries from the public contact form (new → read → replied → closed). | AdminEnquiriesPage; enquiries.status transitions and responded_at/responded_by columns. | Should | Implemented
REC-04 | Admin | As an admin, I want a Payments list showing all online + offline + manual-UPI rows so I can reconcile. | AdminPaymentsPage queries /admin/payments (assumed). | Should | Implemented

## 19. Settings
ID | Role | User story | Acceptance criteria | Priority | Status
SET-01 | Super Admin | As a super_admin, I want to edit clinic settings (name, address, phone, email, GSTIN, UPI VPA, business hours, tax %, cancellation window, refund policy, retention days). | AdminSettingsPage reads/writes clinic_settings JSONB key/value rows; seeded by 01_clinic_settings.sql. | Should | Implemented
SET-02 | System | As the system, I want the patient-facing UPI VPA endpoint to be public so checkout doesn't require auth. | GET /clinic/upi is public; returns {upi_id, upi_display_name}. | Must | Implemented

## 20. Cart
ID | Role | User story | Acceptance criteria | Priority | Status
CRT-01 | Patient | As a patient, I want my cart contents to persist across reloads so I don't lose my selection. | Zustand useCartStore persisted to localStorage key 'arogya-cart'. | Must | Implemented
CRT-02 | Patient | As a patient on the cart page, I want to update quantities or remove items before checkout. | CartPage uses useCartStore { addItem, removeItem, updateQuantity, clear }. | Must | Implemented
CRT-03 | Patient | As a patient, I want a header badge that shows my cart count so I never forget what I added. | Header reads useCartStore().count() and renders badge. | Should | Implemented

## 21. Cross-cutting - NFR
ID | Role | User story | Acceptance criteria | Priority | Status
NFR-01 | System | As the system, I want all booking + invoice numbers generated in Asia/Kolkata so the month suffix matches local time. | Triggers generate_booking_code + generate_invoice_number use AT TIME ZONE 'Asia/Kolkata'. | Must | Implemented
NFR-02 | System | As the system, I want a global rate limit (200/min/IP) and a stricter limit (5/min/IP) on public write endpoints so we resist abuse. | express-rate-limit generalLimiter on all routes; publicWriteLimiter on POST /enquiries + POST /reviews. | Must | Implemented
NFR-03 | System | As the system, I want sensitive fields scrubbed from logs (authorization header, password*, token). | Pino redaction list configured in lib/logger.ts. | Must | Implemented
NFR-04 | System | As the system, I want every DB write that spans multiple tables (booking + items + invoice + payment) inside a single transaction. | transaction() helper wraps BEGIN/COMMIT/ROLLBACK; all booking creation paths use it. | Must | Implemented
NFR-05 | System | As the system, I want frontend hooks to invalidate every affected cache key on a mutation so admin + patient views stay in sync. | Documented in memory feedback_keep_models_in_sync; e.g. useCreateServiceCategory invalidates 3 keys. | Must | Implemented
NFR-06 | System | As the system, I want a startup env-validation gate so missing JWT_SECRET / DATABASE_URL crashes early rather than at first request. | config/env.ts Zod-validates required vars; throws on startup. | Must | Implemented
NFR-07 | System | As the system, I want errorHandler to translate Zod / Multer / pg constraint errors into stable HTTP codes with column-aware messages. | errorHandler.ts maps ZodError→400, MulterError→413/400, 23505→409, 23503/23502/23514→400, 42703/42P01→500 with 'pnpm db:migrate' hint. | Must | Implemented
NFR-08 | System | As the system, I want a feature flag (VITE_PHASE_2_ENABLED) to gate the entire patient + admin Phase-2 surface so we can ship Phase-1 marketing first. | PHASE_2_ENABLED gate in App.tsx wraps Phase-2 routes. | Should | Implemented

## All stories
Module | ID | Role | User story | Acceptance criteria | Priority | Status
1. Public Marketing Site | PUB-01 | Visitor | As a visitor, I want a homepage with hero, services snapshot, doctors snapshot, testimonials, and contact CTA so I can quickly understand what the clinic offers. | Hero with clinic name + tagline; sections for services, doctors, departments, reviews; bilingual EN/BN service names; CTA buttons for Book / Call / WhatsApp. | Must | Implemented
1. Public Marketing Site | PUB-02 | Visitor | As a visitor, I want to browse all diagnostic services and health packages filtered by category and free-text search so I can find what I need. | GET /services?category_slug=&q= returns active services only; ILIKE on name; ordered by display_order; max 200 results. | Must | Implemented
1. Public Marketing Site | PUB-03 | Visitor | As a visitor, I want a service detail page with description, prep instructions, sample type, turnaround time and price so I can decide before booking. | GET /services/:slug; renders full_details, prep_instructions, sample_type, report_turnaround_hours, price; Book Test CTA adds to cart. | Must | Implemented
1. Public Marketing Site | PUB-04 | Visitor | As a visitor, I want to browse all verified doctors filtered by department and search so I can pick the right specialist. | GET /doctors?department_id=&q= filters role=doctor + is_verified + is_active; ordered by rating_avg desc; LIMIT 100. | Must | Implemented
1. Public Marketing Site | PUB-05 | Visitor | As a visitor, I want a doctor profile page with photo, qualifications, departments, consulting centers, schedule preview and reviews so I can choose confidently. | GET /doctors/:id + GET /reviews?doctor_id=; photo via public /doctors/:id/photo blob; reviews limited to status=approved. | Must | Implemented
1. Public Marketing Site | PUB-06 | Visitor | As a visitor, I want to browse clinical departments and their associated doctors so I can navigate by speciality. | GET /departments + GET /departments/:slug; active departments only; ordered by display_order. | Should | Implemented
1. Public Marketing Site | PUB-07 | Visitor | As a visitor, I want a contact form to send the clinic an enquiry without signing up so I can ask questions easily. | POST /enquiries with name/email/phone/subject/message; rate-limited 5/min/IP; inserts row with status=new. | Must | Implemented
1. Public Marketing Site | PUB-08 | Visitor | As a visitor, I want to leave feedback / a review for the clinic or a doctor so future patients can read it. | POST /reviews with star rating + text; status=pending (admin moderation); rate-limited 5/min/IP. | Should | Implemented
1. Public Marketing Site | PUB-09 | Visitor | As a visitor, I want privacy and terms pages so I can understand how my data is used. | Static pages at /privacy and /terms accessible without login. | Should | Implemented
1. Public Marketing Site | PUB-10 | Visitor | As a visitor, I want a Book Home Visit CTA in the header so I can start a home-collection booking immediately. | Header button sets cartStore.preferredVisitType='home_visit' and navigates to /services?mode=home_visit; Services page shows banner with reset option. | Should | Implemented
2. Authentication & Identity | AUTH-01 | Patient | As a new patient, I want to sign up with first/last name, mobile, optional email and password so I can manage my bookings. | POST /auth/signup; mobile regex ^[6-9]\d{9}$; password ≥6; rejects duplicate mobile/email; returns JWT + user. | Must | Implemented
2. Authentication & Identity | AUTH-02 | Patient | As an existing patient, I want to log in with email and password so I can access my dashboard. | POST /auth/login; bcrypt verify; checks is_active && is_login_enabled; updates last_login_at; returns JWT + user. | Must | Implemented
2. Authentication & Identity | AUTH-03 | Patient | As a patient without a password, I want to log in with mobile + OTP so I don't need to remember credentials. | POST /auth/otp/send returns 6-digit code (debug_code in non-prod); POST /auth/otp/verify accepts code + optional names; auto-creates patient row if mobile is new. | Must | Implemented (OTP via SMS provider TODO)
2. Authentication & Identity | AUTH-04 | Patient | As a logged-in patient, I want to view my profile (name, mobile, email, DOB, gender, default address) so I can keep it current. | GET /auth/me returns full user row; rendered on /dashboard/profile. | Must | Implemented
2. Authentication & Identity | AUTH-05 | Patient | As a logged-in patient, I want to update my profile fields including default address JSON so future bookings prefill correctly. | PATCH /me with profileUpdateSchema; dynamic SET builder; default_address stored as JSONB. | Must | Implemented
2. Authentication & Identity | AUTH-06 | Patient | As a logged-in patient, I want to change my password so I can rotate credentials. | POST /auth/change-password; current_password verified if existing hash; new_password hashed via bcrypt. | Should | Implemented
2. Authentication & Identity | AUTH-07 | Patient | As a logged-in patient, I want to log out from the header dropdown so my JWT is cleared from the device. | Best-effort POST /auth/logout + clears arogya-jwt localStorage + zustand state. | Must | Implemented
2. Authentication & Identity | AUTH-08 | Admin | As an admin/super_admin, I want a separate /admin/login route so my login experience is distinct from the patient flow. | AdminLoginPage; same POST /auth/login; on success redirects to /admin and RequireAuth checks role admin¦super_admin. | Must | Implemented
2. Authentication & Identity | AUTH-09 | Any role | As any logged-in user, I want my JWT to be re-validated on every request so revoking an account takes effect immediately. | requireAuth middleware re-reads users row by sub claim; sets req.user; rejects with 403 ACCOUNT_DISABLED when is_active=false. | Must | Implemented
2. Authentication & Identity | AUTH-10 | Patient | As a patient who got auto-logged out (401), I want my JWT cleared automatically so /auth/me doesn't loop. | Axios response interceptor clears token on 401 then propagates the error. | Should | Implemented
3. Patient Dashboard | PD-01 | Patient | As a patient, I want a dashboard overview showing upcoming bookings, pending payments and recent reports so I get a one-glance status. | DashboardOverviewPage uses useMyBookings()/useMyReports() to render KPI cards + next-appointment + recent-reports. | Must | Implemented
3. Patient Dashboard | PD-02 | Patient | As a patient, I want a dedicated Appointments page listing my doctor bookings so I can track them. | GET /bookings filtered by booking_type=doctor_appointment; each row shows doctor_name, speciality, center, status badge. | Must | Implemented
3. Patient Dashboard | PD-03 | Patient | As a patient, I want a dedicated Tests page listing my test/package bookings so I can track sample collection and results. | GET /bookings filtered to test_booking; row shows items_summary, collection_status, reports_count. | Must | Implemented
3. Patient Dashboard | PD-04 | Patient | As a patient, I want a combined My Bookings page if I prefer one stream view. | MyBookingsPage at /dashboard/bookings unifies both booking types ordered by scheduled_date desc. | Should | Implemented
3. Patient Dashboard | PD-05 | Patient | As a patient, I want to open a booking detail page from any list to see items, payment status, address, advance/balance and reports. | GET /bookings/:id; ownership-checked; renders items, payments, active reports with download links. | Must | Implemented
3. Patient Dashboard | PD-06 | Patient | As a patient, I want to cancel an upcoming booking from its detail page if my plans change. | POST /bookings/:id/cancel sets booking_status=cancelled and records cancelled_at + optional reason. | Must | Implemented
3. Patient Dashboard | PD-07 | Patient | As a patient, I want a Reports page that lists all my lab results across bookings so I can find them in one place. | GET /reports patient-scoped; ReportsPage thumbnails + download via signed URL. | Must | Implemented
3. Patient Dashboard | PD-08 | Patient | As a patient, I want a clear status sub-line like 'Advance ₹100 paid · Balance ₹100 due at visit' instead of generic status text. | BookingStatusBadge takes paymentStatus + totalAmount + advanceAmount and renders contextual sub-line; threaded through all dashboard pages. | Should | Implemented
4. Doctor Appointment Booking | DA-01 | Patient | As a patient, I want to pick a doctor's available date and time slot from a live calendar so I don't book a conflicting slot. | GET /doctors/:id/slots?date=&center_id=&visit_type=; live generator reads doctor_centers.schedule, subtracts existing bookings + doctor_unavailability; returns {time, available, reason}. | Must | Implemented
4. Doctor Appointment Booking | DA-02 | Patient | As a patient, I want to enter or confirm my contact details and address for the appointment. | Step 2 of BookDoctorPage uses patientInfoSchema; prefills from useAuthStore user when present. | Must | Implemented
4. Doctor Appointment Booking | DA-03 | Patient | As a patient, I want a clear breakdown of consultation fee, advance (50%) and balance so I know what I'm paying. | subtotal = doctor.consultation_fee; advance = round(total/2); balance = total - advance; rendered in checkout summary. | Must | Implemented
4. Doctor Appointment Booking | DA-04 | Patient | As a patient, I want to submit the booking with a UPI payment proof image/PDF so my slot is locked immediately. | POST /bookings/doctor-appointment (multipart) inserts bookings + booking_items(doctor_consultation) + invoices (trigger numbers it) + payments(upi_manual, captured, verified_at=NULL) in one transaction. | Must | Implemented
4. Doctor Appointment Booking | DA-05 | Patient | As a patient, I want a no-consulting-center guard so I'm not allowed to book a doctor whose schedule isn't set up yet. | BookDoctorPage shows friendly message when doctor.centers[] is empty. | Should | Implemented
5. Test / Package Booking | TB-01 | Patient | As a patient, I want to add multiple tests/packages to a cart with quantities so I can check out in one go. | useCartStore items[] persists to localStorage 'arogya-cart'; supports addItem, removeItem, updateQuantity, subtotal, count. | Must | Implemented
5. Test / Package Booking | TB-02 | Patient | As a patient, I want to pick in-clinic vs home collection per booking so I can choose how the sample is taken. | Step 2 of BookTestPage switches visit_type; home_visit branch reveals address + pincode check + slot picker. | Must | Implemented
5. Test / Package Booking | TB-03 | Patient | As a patient, I want to enter my pincode and instantly see if home collection is serviceable + the home-visit charge. | GET /serviceable-pincodes/check?pincode= validates regex; returns {serviceable, city, home_visit_charge, collection_lead_time_hours}. | Must | Implemented
5. Test / Package Booking | TB-04 | Patient | As a patient, I want to pick a home collection time slot if my pincode is serviceable. | GET /home-collection/slots?date=&pincode= currently returns hardcoded 8-slot grid (STUB); hook is enabled only when pincode confirmed. | Must | Stub (hardcoded slots)
5. Test / Package Booking | TB-05 | Patient | As a patient, I want a clear breakdown showing items × qty, subtotal, home-visit charge, total, advance and balance. | Step 3 renders summary; advance = round((subtotal + home_visit_charge)/2). | Must | Implemented
5. Test / Package Booking | TB-06 | Patient | As a patient, I want to submit my test booking with a UPI payment proof so my slot is reserved immediately and the invoice is auto-generated. | POST /bookings/test (multipart) inserts bookings + N booking_items + invoices + payments(upi_manual) atomically; redirects to /payment/callback. | Must | Implemented
5. Test / Package Booking | TB-07 | Patient | As a patient, I want my home-visit preference to survive navigation from Services → Cart → Booking. | cartStore.preferredVisitType persists; BookTestPage reads it for initial visit-type state. | Should | Implemented
6. Payments (Manual UPI) | PAY-01 | Patient | As a patient at checkout, I want to see the clinic's UPI VPA + QR code so I can pay from any UPI app. | GET /clinic/upi returns {upi_id, upi_display_name} from clinic_settings; UpiPaymentModal renders QR via react-qr-code and copy-VPA button. | Must | Implemented
6. Payments (Manual UPI) | PAY-02 | Patient | As a patient, I want to attach a screenshot or PDF of the UPI confirmation (with optional UTR) so my booking is captured. | FormData: payment_proof (≤5 MB, jpeg/png/webp/pdf) + data (JSON booking payload) + optional upi_reference; backend validates via validateProofFile(). | Must | Implemented
6. Payments (Manual UPI) | PAY-03 | Patient | As a patient, I want to view the proof I uploaded inside my booking detail page so I can confirm what I sent. | GET /payments/:id/proof streams BYTEA (own-only); ProofPreview renders image or PDF embed. | Should | Implemented
6. Payments (Manual UPI) | PAY-04 | Admin | As an admin, I want a Payment Re-Verify queue listing all upi_manual payments with verified_at IS NULL so I can clear them at sample-collection / clinic-visit. | GET /admin/payments/pending-re-verify; partial index payments_pending_reverify_idx; AdminLayout bell badge shows count. | Must | Implemented
6. Payments (Manual UPI) | PAY-05 | Admin | As an admin, I want to view the uploaded proof in a large modal alongside booking metadata + optional notes textarea before approving. | ReVerifyPaymentModal with proof full-bleed + booking sidebar + notes; calls GET /admin/payments/:id/proof. | Must | Implemented
6. Payments (Manual UPI) | PAY-06 | Admin | As an admin, I want re-verify to be idempotent so double-clicking doesn't break anything. | POST /admin/payments/:paymentId/re-verify uses CTE WHERE verified_at IS NULL; second call returns already-verified row. | Must | Implemented
6. Payments (Manual UPI) | PAY-07 | Patient | As a patient, I want my booking status to read 'In progress' until admin re-verifies, then automatically update to 'Confirmed'. | Booking status transitions in_progress → confirmed; verified_at populated; cache invalidation propagates to patient hooks. | Must | Implemented
6. Payments (Manual UPI) | PAY-08 | Admin | As an admin, I want to record an offline payment (cash, UPI QR offline, card swipe, cheque) against an existing booking so partial payments can be added later. | POST /admin/bookings/:id/payments uses FOR UPDATE lock; recomputes paid/balance/payment_status from SUM(amount-refunded_amount). | Must | Implemented
6. Payments (Manual UPI) | PAY-09 | System | As the system, I want to keep Razorpay stubs for later reintroduction so we can switch back without rewriting. | POST /bookings/:id/confirm-payment-stub + POST /payments/create-order + POST /webhooks/razorpay (no signature verify yet) all preserved. | Should | Preserved as stub
7. Reports / Lab Results | RPT-01 | Admin | As an admin, I want to look up a booking by its human-readable booking_code (AROGYA-TEST-YYYYMM-NNNNNN) so I can upload reports without typing numeric IDs. | GET /admin/booking-lookup?code=; returns id + patient_snapshot + items_summary + doctor_name. | Must | Implemented
7. Reports / Lab Results | RPT-02 | Admin | As an admin, I want to upload multiple report files (PDF/image/DICOM/Word/ZIP - any format) for a booking with a chosen report_type. | POST /admin/bookings/:bookingId/reports (multer 25 MB cap, no MIME whitelist); version = MAX+1 per booking; no soft-disable of prior versions. | Must | Implemented
7. Reports / Lab Results | RPT-03 | Admin | As an admin, I want a standalone /admin/reports page that lists recent reports across bookings with thumbnails + preview + delete actions. | GET /admin/reports?q=&limit= joins reports + bookings; AdminReportsPage shows 48×48 thumbnail or file icon, action buttons. | Should | Implemented
7. Reports / Lab Results | RPT-04 | Admin | As an admin, I want to soft-delete a report so it disappears from the patient's view but stays for audit. | DELETE /admin/reports/:reportId sets is_active=FALSE; cache invalidation hits admin list + patient myReports + booking detail. | Must | Implemented
7. Reports / Lab Results | RPT-05 | Patient | As a patient, I want to download my report via a short-lived signed URL so the file is protected. | GET /reports/:id/download (uploads route) returns {url, expires_in:900} via storage.getSignedUrl; downloadReport() opens new tab. | Must | Implemented
7. Reports / Lab Results | RPT-06 | System | As the system, I want reports for walk-in bookings to be allowed even when no patient user exists. | Migration 0023: reports.patient_user_id is NULLABLE; ownership is via booking_id; upload handler still populates when booking has a user. | Must | Implemented
8. Invoices | INV-01 | System | As the system, I want every booking (online doctor / online test / walk-in) to auto-create exactly one invoice with a generated number on INSERT. | INSERT invoices(invoice_number='') inside the same booking transaction; generate_invoice_number trigger fills INV-YYYYMM-NNNNNN (Asia/Kolkata). | Must | Implemented
8. Invoices | INV-02 | Patient | As a patient, I want to download my own invoice as a PDF from my booking detail page. | GET /bookings/:id/invoice.pdf (own-only); shared streamInvoicePdf() helper; A4 PDF via pdfkit. | Must | Implemented
8. Invoices | INV-03 | Admin | As an admin, I want to list all invoices with filters (type/origin/from/to/free-text) so I can find them quickly. | GET /admin/invoices?type=&origin=&from=&to=&q= joins invoices + bookings; max 500 rows; ILIKE on invoice_number, booking_code, patient_snapshot JSON keys. | Must | Implemented
8. Invoices | INV-04 | Admin | As an admin, I want per-row download of the invoice PDF from the invoices list. | GET /admin/bookings/:id/invoice.pdf delegates to streamInvoicePdf(); same PDF as patient download. | Must | Implemented
8. Invoices | INV-05 | System | As the system, I want the invoice header/footer to reflect current clinic settings (name, address, phone, email, GSTIN). | PDF reads clinic_settings; clinic_address JSON flattened to 'line1, line2, city, state, pincode'. | Should | Implemented
9. Admin Dashboard & Analytics | DSH-01 | Admin | As an admin, I want a dashboard with today's bookings, today's revenue, pending reports, new patients this week and yesterday comparison. | GET /admin/dashboard returns kpis + schedule; computes today/yesterday boundaries in Asia/Kolkata; revenue from payments (captured-refunded). | Must | Implemented
9. Admin Dashboard & Analytics | DSH-02 | Admin | As an admin, I want the dashboard to auto-refresh so I can keep it open as a live operations screen. | useAdminDashboard refetchInterval: 60_000 ms. | Should | Implemented
9. Admin Dashboard & Analytics | DSH-03 | Admin | As an admin, I want today's schedule of the next 10 bookings with doctor + items summary on the dashboard. | schedule[] subquery returns 10 rows with inline doctor_name and items_summary via string_agg. | Must | Implemented
9. Admin Dashboard & Analytics | DSH-04 | Admin | As an admin, I want an Analytics page showing daily revenue + booking trend, top services, type/origin/status/payment-method distributions over the last N days. | GET /admin/analytics?days=N (1-365); Promise.all-fans-out 7 queries; generate_series ensures empty days are charted. | Should | Implemented
9. Admin Dashboard & Analytics | DSH-05 | Admin | As an admin, I want to export analytics to CSV so I can share with stakeholders. | Multi-section CSV built client-side via Blob URL (KPIs + daily trend + top services + status + payment methods). | Should | Implemented
9. Admin Dashboard & Analytics | DSH-06 | Admin | As an admin, I want the heavy analytics charts lazy-loaded so the rest of the app stays light. | AnalyticsPage uses React.lazy in App.tsx; chunk is ~119 kB gzipped. | Could | Implemented
10. Admin Bookings | AB-01 | Admin | As an admin, I want a filterable bookings list (by type, origin, status, free-text) so I can find rows fast. | GET /admin/bookings?type=&origin=&status=&q=&visit_type=; subqueries inline doctor_name + items_summary; LIMIT 200 ORDER BY created_at desc. | Must | Implemented
10. Admin Bookings | AB-02 | Admin | As an admin, I want to open a booking detail page showing items, payments, active reports, advance/balance and the patient snapshot. | GET /admin/bookings/:id; full booking + items + payments + active reports. | Must | Implemented
10. Admin Bookings | AB-03 | Admin | As an admin, I want to change a booking's status (pending_payment / confirmed / in_progress / completed / cancelled / no_show) from a color-coded dropdown both in the list and the detail sidebar. | PATCH /admin/bookings/:id/status; BookingStatusSelect compact + default variants; invalidates admin + patient caches. | Must | Implemented
10. Admin Bookings | AB-04 | Admin | As an admin, I want to filter by visit_type (in_clinic vs home_visit) so I can split the worklist. | visit_type filter on /admin/bookings and /admin/invoices; SELECT also returns b.visit_type for origin pill. | Should | Implemented
11. Walk-in Bills | WB-01 | Admin | As a receptionist, I want a Create Walk-in Bill page where I can capture patient (snapshot or existing user), N line items (catalog or custom), and optional payment in one form. | POST /admin/walk-in-bills with discriminated-union walkInItemSchema; single transaction creates booking + items + optional payment + invoice. | Must | Implemented
11. Walk-in Bills | WB-02 | Admin | As a receptionist, I want walk-in bookings to use today's date/time and skip slot generation so I can bill quickly. | INSERT bookings with booking_origin='walk_in', visit_type='in_clinic', scheduled_date=today, scheduled_start_time=now, collection_status='not_required'. | Must | Implemented
11. Walk-in Bills | WB-03 | Admin | As a receptionist, I want the bill to automatically compute subtotal, total, paid, balance, payment_status and booking_status so I don't make arithmetic mistakes. | Backend computes payment_status (pending¦partial¦paid) and booking_status (completed if paid in full else in_progress). | Must | Implemented
11. Walk-in Bills | WB-04 | Admin | As a receptionist, I want offline payment captured atomically with the booking so the invoice numbers correctly. | INSERT payments(payment_source='offline', payment_status='captured', collected_by_user_id=req.user.id) when payment.amount > 0; invoice trigger fires. | Must | Implemented
12. Catalog: Categories | CAT-01 | Admin | As an admin, I want full CRUD over service categories with auto-slug, duplicate detection, soft delete, and a doctors/services count badge. | GET/POST/PATCH/DELETE /admin/service-categories[/:id]; FK on services.category_id is ON DELETE RESTRICT so deletes are soft (is_active=FALSE). | Must | Implemented
12. Catalog: Services | CAT-02 | Admin | As an admin, I want full CRUD over services + health packages with category dropdown, auto-slug, package toggle (package_service_ids + discount %), and soft delete. | GET/POST/PATCH/DELETE /admin/services[/:id]; services_package_consistency_chk enforced by always sending [] for package_service_ids on package rows. | Must | Implemented
12. Catalog: Services | CAT-03 | Admin | As an admin, I want unique slug + test_key conflicts surfaced as friendly 409 messages so I know which field collides. | Pre-checks both UNIQUE constraints and returns 409 DUPLICATE with the offending column. | Should | Implemented
12. Catalog: Departments | CAT-04 | Admin | As an admin, I want CRUD over departments with auto-slug, doctor count, and soft delete. | GET/POST/PATCH/DELETE /admin/departments[/:id]; FK users.department_id ON DELETE SET NULL but soft-delete pattern used. | Must | Implemented
12. Catalog: Pincodes | CAT-05 | Admin | As an admin, I want CRUD over serviceable pincodes (with city/state/zone/home_visit_charge/lead_time) so home collection is correctly scoped. | GET/POST/PATCH/DELETE /admin/serviceable-pincodes[/:id]; pincode field disabled in edit (natural key); soft delete. | Must | Implemented
12. Catalog: Pincodes | CAT-06 | System | As the system, I want a deactivated pincode to immediately stop being bookable for home collection. | Public /serviceable-pincodes/check filters WHERE is_active=TRUE; no extra work needed. | Must | Implemented
13. Doctor Management | DR-01 | Admin | As an admin, I want to list all doctors (including inactive) with department filter, search, photo avatar, and centers count. | GET /admin/doctors?q=&department_id=&is_active=; centers_count subquery; DoctorAvatar per row. | Must | Implemented
13. Doctor Management | DR-02 | Admin | As an admin, I want to add a doctor with profile (name, speciality, qualifications, consultation fee, about, department) and one or more consulting centers in a single submit. | POST /admin/doctors with nested centers[]; transaction inserts users(role=doctor,is_login_enabled=FALSE) + N doctor_centers. | Must | Implemented
13. Doctor Management | DR-03 | Admin | As an admin, I want to upload a doctor's profile photo and have it served back at a public URL for marketing pages. | POST /admin/doctors/:id/photo (5 MB, JPG/PNG/WEBP); writes BYTEA + MIME; GET /doctors/:id/photo public stream with Cache-Control max-age=300. | Must | Implemented
13. Doctor Management | DR-04 | Admin | As an admin, I want to add/edit/soft-delete a doctor's consulting centers including a visual Weekly Schedule editor with slot duration, buffer, lunch. | POST /admin/doctors/:id/centers, PATCH/DELETE /admin/centers/:centerId; WeeklyScheduleEditor emits WeeklySchedule JSON matching doctor_centers.schedule shape. | Must | Implemented
13. Doctor Management | DR-05 | Admin | As an admin, I want a separate home-visit schedule per center so a doctor can do clinic visits on some days and home visits on others. | doctor_centers.home_visit_schedule JSONB; reads in slot generator when visit_type=home_visit. | Should | Implemented
14. Slot Generation | SLOT-01 | System | As the system, I want to generate slots live from the doctor's schedule, subtracting existing bookings and unavailability blocks, so admins manage availability through the schedule editor. | Slot generator reads schedule/home_visit_schedule for weekday, generates from {start,end,slot_minutes,buffer_minutes,lunch_start,lunch_end}, subtracts active bookings + doctor_unavailability. | Must | Implemented
14. Slot Generation | SLOT-02 | Admin | As an admin, I want to block whole days or specific slots for a doctor via doctor_unavailability so vacations and emergencies are respected. | doctor_unavailability rows: NULL slot_start_time = whole day; NULL doctor_center_id = all centers. | Should | DB ready, no admin UI yet
14. Slot Generation | SLOT-03 | System | As the system, I want to prevent double-booking via a partial unique index on (doctor_user_id, doctor_center_id, scheduled_date, scheduled_start_time). | uq_active_slot partial unique index covers booking_status IN (draft, pending_payment, confirmed, in_progress). | Must | Implemented
14. Slot Generation | SLOT-04 | System | As the system, I want a cron to expire stale drafts so slot locks are released. | Flag stale draft bookings whose slot_locked_until has passed to cancelled. | Should | TODO (noted in migration)
15. Home Collection | HC-01 | Admin | As an admin, I want CRUD over home collector accounts (phlebotomists) including name, mobile, DOB (for age), gender, photo, active toggle. | GET/POST/PATCH/DELETE /admin/collectors; users row with role='patient'+admin_role='collector' or similar; photo uploaded as BYTEA via /admin/collectors/:id/photo. | Must | Implemented
15. Home Collection | HC-02 | Admin | As an admin, I want a Home Collection Board (Kanban) showing each home-visit booking by collection_status so I can dispatch fast. | HomeCollectionBoardPage groups bookings by collection_status: not_assigned → assigned → en_route → collected → received_at_lab. | Must | Implemented
15. Home Collection | HC-03 | Admin | As an admin, I want to assign a collector to a not_assigned booking via a dropdown directly on the board. | useUpdateCollection mutation sets collection_status='assigned' + assigned_staff_user_id; useCollectionStaff() feeds dropdown. | Must | Implemented
15. Home Collection | HC-04 | Admin | As an admin, I want to progress a collection through stages so the patient and lab are kept in sync. | PATCH /admin/home-collections/:id transitions collection_status through assigned → en_route → collected → received_at_lab. | Must | Implemented
15. Home Collection | HC-05 | Patient | As a patient, I want to see the assigned collector's name, age, phone and photo on my booking page so I know who is coming. | Booking detail surfaces assigned_staff metadata (full name, age computed from DOB, mobile, photo URL). | Should | Implemented
16. Notifications | NOTIF-01 | System | As the system, I want a notifications table that supports both per-user and admin-broadcast rows so the bell can show targeted + clinic-wide events. | Migration 0026: notifications + notification_reads; audience IN (admin, patient, collector); partial indexes for hot paths (unread + admin broadcasts). | Must | Implemented
16. Notifications | NOTIF-02 | Admin / Patient | As an admin or patient, I want a bell icon in my header with an unread badge so I can see new events at a glance. | NotificationBell variants light (patient header) / dark (admin layout); badge shows count capped at 9+. | Must | Implemented
16. Notifications | NOTIF-03 | Admin / Patient | As an admin or patient, I want the bell to poll the server every 30s and refetch on tab focus + on open so I see fresh events. | useMyNotifications polls; dropdown open also invalidates ['notifications','mine']. | Should | Implemented
16. Notifications | NOTIF-04 | Admin / Patient | As an admin or patient, I want to click a notification to mark it read and deep-link to the related entity. | useMarkNotificationRead; broadcasts use notification_reads table; non-broadcast use read_at column; click triggers Link to n.link. | Must | Implemented
16. Notifications | NOTIF-05 | Admin / Patient | As an admin or patient, I want a Mark All Read button to bulk-clear my unread count. | useMarkAllNotificationsRead. | Should | Implemented
16. Notifications | NOTIF-06 | System | As the system, I want notifications fired for proof_submitted, reverified, collector_assigned, collection_status_changed so users are informed of state changes. | Backend domain events INSERT notifications with appropriate event + link + audience. | Must | Implemented
17. Audit Log | AUDIT-01 | System | As the system, I want every successful authenticated mutating request (POST/PATCH/PUT/DELETE 2xx) automatically logged with actor, action, entity, IP and user-agent. | auditLogMiddleware hooks res.on('finish'); classify() derives action from URL (e.g. services.create, payments.re-verify); SKIP_PATTERNS exclude auth/me/health/webhooks. | Must | Implemented
17. Audit Log | AUDIT-02 | Super Admin | As a super_admin, I want an admin audit-log page to review who did what when. | AdminAuditLogPage uses GET /admin/audit-log; filters by actor, action, entity, date range. | Should | Implemented
17. Audit Log | AUDIT-03 | System | As the system, I want audit failures to never break the real action. | INSERT is fire-and-forget after res.finish; errors are logged via pino, not propagated. | Must | Implemented
18. Patients Records | REC-01 | Admin | As an admin, I want a Patients page listing all patient users with mobile, last login, booking count so I can support them. | AdminPatientsPage queries /admin/patients (assumed). | Should | Implemented
18. Patients Records | REC-02 | Admin | As an admin, I want to moderate reviews (pending → approved/rejected/hidden) with optional rejection_reason and clinic_reply. | AdminFeedbackPage reads pending reviews; reviews table tracks status, clinic_reply, replied_at, replied_by. | Should | Implemented
18. Patients Records | REC-03 | Admin | As an admin, I want to triage enquiries from the public contact form (new → read → replied → closed). | AdminEnquiriesPage; enquiries.status transitions and responded_at/responded_by columns. | Should | Implemented
18. Patients Records | REC-04 | Admin | As an admin, I want a Payments list showing all online + offline + manual-UPI rows so I can reconcile. | AdminPaymentsPage queries /admin/payments (assumed). | Should | Implemented
19. Settings | SET-01 | Super Admin | As a super_admin, I want to edit clinic settings (name, address, phone, email, GSTIN, UPI VPA, business hours, tax %, cancellation window, refund policy, retention days). | AdminSettingsPage reads/writes clinic_settings JSONB key/value rows; seeded by 01_clinic_settings.sql. | Should | Implemented
19. Settings | SET-02 | System | As the system, I want the patient-facing UPI VPA endpoint to be public so checkout doesn't require auth. | GET /clinic/upi is public; returns {upi_id, upi_display_name}. | Must | Implemented
20. Cart | CRT-01 | Patient | As a patient, I want my cart contents to persist across reloads so I don't lose my selection. | Zustand useCartStore persisted to localStorage key 'arogya-cart'. | Must | Implemented
20. Cart | CRT-02 | Patient | As a patient on the cart page, I want to update quantities or remove items before checkout. | CartPage uses useCartStore { addItem, removeItem, updateQuantity, clear }. | Must | Implemented
20. Cart | CRT-03 | Patient | As a patient, I want a header badge that shows my cart count so I never forget what I added. | Header reads useCartStore().count() and renders badge. | Should | Implemented
21. Cross-cutting / NFR | NFR-01 | System | As the system, I want all booking + invoice numbers generated in Asia/Kolkata so the month suffix matches local time. | Triggers generate_booking_code + generate_invoice_number use AT TIME ZONE 'Asia/Kolkata'. | Must | Implemented
21. Cross-cutting / NFR | NFR-02 | System | As the system, I want a global rate limit (200/min/IP) and a stricter limit (5/min/IP) on public write endpoints so we resist abuse. | express-rate-limit generalLimiter on all routes; publicWriteLimiter on POST /enquiries + POST /reviews. | Must | Implemented
21. Cross-cutting / NFR | NFR-03 | System | As the system, I want sensitive fields scrubbed from logs (authorization header, password*, token). | Pino redaction list configured in lib/logger.ts. | Must | Implemented
21. Cross-cutting / NFR | NFR-04 | System | As the system, I want every DB write that spans multiple tables (booking + items + invoice + payment) inside a single transaction. | transaction() helper wraps BEGIN/COMMIT/ROLLBACK; all booking creation paths use it. | Must | Implemented
21. Cross-cutting / NFR | NFR-05 | System | As the system, I want frontend hooks to invalidate every affected cache key on a mutation so admin + patient views stay in sync. | Documented in memory feedback_keep_models_in_sync; e.g. useCreateServiceCategory invalidates 3 keys. | Must | Implemented
21. Cross-cutting / NFR | NFR-06 | System | As the system, I want a startup env-validation gate so missing JWT_SECRET / DATABASE_URL crashes early rather than at first request. | config/env.ts Zod-validates required vars; throws on startup. | Must | Implemented
21. Cross-cutting / NFR | NFR-07 | System | As the system, I want errorHandler to translate Zod / Multer / pg constraint errors into stable HTTP codes with column-aware messages. | errorHandler.ts maps ZodError→400, MulterError→413/400, 23505→409, 23503/23502/23514→400, 42703/42P01→500 with 'pnpm db:migrate' hint. | Must | Implemented
21. Cross-cutting / NFR | NFR-08 | System | As the system, I want a feature flag (VITE_PHASE_2_ENABLED) to gate the entire patient + admin Phase-2 surface so we can ship Phase-1 marketing first. | PHASE_2_ENABLED gate in App.tsx wraps Phase-2 routes. | Should | Implemented